## OEModule1DecideQuestion
No | QuestionDescription | Category | Option 1 | Option 2 | Option 3 | Option 4 | Answer | Points
1 | End of each day, Approved Passport file numbers must be sent to the Government Press. Based on your intuition / experience, identify the stakeholders who are responsible | Decide 1 | Richard Burbon | Adam Smith | Salma Hyatt | Ayman Shah | Salma Hyatt | 10
2 | End of each day, Approved Passport file numbers must be sent to the Government Press. Based on your intuition / experience, identify the stakeholders who are Accountable | Decide 1 | Salma Hyatt | Adam Smith | Ayman Shah | Richard Burbon | Richard Burbon | 10
3 | End of each day, Approved Passport file numbers must be sent to the Government Press. Based on your intuition / experience, identify the stakeholders who are Consult | Decide 1 | Adam Smith | Salma Hyatt | Richard Burbon | Ayman Shah | Adam Smith | 10
4 | End of each day, Approved Passport file numbers must be sent to the Government Press. Based on your intuition / experience, identify the stakeholders who are Inform | Decide 1 | Richard Burbon | Ayman Shah | Adam Smith | Salma Hyatt | Ayman Shah | 10
5 | Stakeholder Salma Hyatt -- Power | Decide 2 | High | Medium | Low | Null | Low | 5
6 | Stakeholder Salma Hyatt -- Interest | Decide 2 | Low | High | Medium | Null | High | 5
7 | Stakeholder Richard Burbon -- Power | Decide 2 | High | Low | Medium | Null | Medium | 5
8 | Stakeholder Richard Burbon -- Interest | Decide 2 | Medium | Low | High | Null | High | 5
9 | Stakeholder Adam Smith -- Power | Decide 2 | Medium | Low | High | Null | High | 5
10 | Stakeholder Adam Smith -- Interest | Decide 2 | Medium | Low | High | Null | Low | 5
11 | Stakeholder Ayman Shah -- Power | Decide 2 | Medium | Low | High | Null | High | 5
12 | Stakeholder Ayman Shah -- Interest | Decide 2 | Medium | Low | High | Null | Low | 5
13 | Cost of servicing a Passport must always be less than $25. Where would you slot this expectation from the ATLAS Corp Management, as per Kano’s model | Decide 3 | Expected | Exciting | Revealed | Null | Expected | 10
14 | What if a citizen requesting a Passport gets his passport in 20 minutes? From the consumer’s perspective, where would you categorize his/her expectation levels? | Decide 3 | Expected | Exciting | Revealed | Null | Exciting | 10
15 | All scheduled passport appointments had to be cancelled due to an intense weather condition. Where do you see the Service Expectation of the Federal Government in such a scenario? | Decide 3 | Expected | Exciting | Revealed | Null | Revealed | 10

## LearnerUserDataTable
TableName | OEModule2DecideLearnerUserData
Attempt | UserEmail | ProductName | ModuleName | UI-1 | UI-2 | UI-3 | UI-4 | UI-5 | UI-6 | UI-7 | UI-8 | UI-9 | UI-10 | UI-11 | UI-12 | UI-13 | UI-14 | UI-15 | UI-16